## Sheet1
Engineer = | 9 hours/day | 5 days/week |  |  |  | Time | Planned | Actual | Earned
Team(5 Eng) = | 9*5*4*5 = | 900 hours/month |  |  |  | 0 | 0 | 0 | 0
Project Budget = | 10000 hours |  |  |  |  | 6 | 5000 | 7000 | 5500
Project Duration = | 10000/900 =~ | 12 months |  |  |  | 12 | 10000
After 6 Months
Planned Value | 5K hrs | 50% finished
Actual Value | 7K hrs | 55% finished
Earned Value | 5.5K hrs
Project Over Budget ? | Yes | 7K - 5.5K = 1.5K hrs
Project Delayed ? | No | 5K - 5.5K = -0.5K hrs | Early by 500 hrs | 500/(9*5) = | 11 days